## Sheet1
| 19th June | [6 empty] | 26th June | [6 empty] | 3rd July | [6 empty] | 10th July | [6 empty] | 17th July | [6 empty] | 24th July
Tasks | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Receive Arduino 101 | bar: 19th June W
Order parts in inventory list | bar: 19th June T to 19th June F
Get RPi reading Xbox controller | bar: 19th June S to 26th June M
Confirm transeiver operation on Pi and Arduino | bar: 26th June T
Get Pi transmitting controller data | bar: 26th June W to 26th June S
Get arduino receiving data | bar: 26th June W to 26th June S
Receive ordered parts | bar: 26th June M to 26th June F
Drone construction -frame | bar: 3rd July M; 3rd July F to 3rd July S
Drone construction - check motors | bar: 3rd July M; 3rd July F to 3rd July S
Drone construction - soldering escs and pdb | bar: 3rd July T to 3rd July W
Check motors work | bar: 3rd July W to 3rd July F
Recover from eye surgery | bar: 10th July M to 10th July S
PID control | bar: 10th July S to 17th July M
Intergrate RC setpoints to PID | bar: 10th July S to 17th July T
Get IMU to work | bar: 17th July T to 17th July F
Integrate IMU setpoints to PID | bar: 17th July F
Integrate motor control to sketch | bar: 17th July F to 17th July S
Tune PID values | bar: 17th July F to 24th July T
Achieve stable flight | bar: 17th July F to 24th July T
Work on stretch goals | bar: 24th July W to 24th July T
Submit! | bar: 24th July F